## CMS
Ref # | User Story | Category | Priority | User Permissioning | [6 empty] | Order of Importance | ForumeOne LoE Estimates (0-8) | Beta Release Completion | Notes
|  |  |  | Public | Members | SAB | SC | Research Team | Admins | Collaborators
R1 | I want to read about AGRODEP mission, objectives, management structure, donors, milestones | general | high | x | x | x | x | x | x | x | 11 | 3 | 100% | content copied over from existing website - improve layout of upcoming/past events pages
R2 | I want to consult AGRODEP member directory (incl. affiliations, roles, e-mails and phone numbers, bios and photos) | directory | high |  | x | x | x | x | x | x | 14 | 2 | 100% | need to migrate member profiles and create corresponding user accounts - need faceted search tools on Member Directory page and design improvements
R3 | I want to update and restrict public access to my contact information | directory | high |  | x | x | x | x | x | x | 15 | 3 | 100%
R4 | I want to subscribe/unsubscribe to AGRODEP mailing lists | directory | medium |  | x | x | x | x | x | x | 43 | 2 | 100% | similar features (and more) available through MailChimp - integration with Drupal needed
R5 | I want to see a journal of my contributions and of other members' contributions (comments, submissions, discussion posts, etc..) | directory | medium |  | x | x | x | x | x | x | 37 | 5 | 100% | through "My AGRODEP" - should also be viewable on every member's profile
R6 | I want to consult AGRODEP calendar of events (past and upcoming events, incl. planned committee and management meetings) | events | high | x | x | x | x | x | x | x | 12 | 3 | 100% | need design improvements
R7 | I want to view past event summaries and output (presentations, list of attendants, papers, training materials, and or meeting notes and decisions made) | events | medium |  | x | x | x | x | x | x | 13 | 5 | 100% | content is ready - need design improvements
R8 | I want to register to new events (fill out registration form) | events | high |  | x | x | x | x |  | x | 16 | 3 | 100% | we want this built-in to Drupal
R8.1 | I want to upload required registration documents | events | high |  | x | x | x | x |  | x | 17 | 3 | 100%
R9 | I want to check on the status of my registration(s) and retrieve VISA application letters | events | medium |  | x | x | x | x |  | x | 18 | 3 | 50% | status currently does not show "applied" or "registered", only "attended".
R10 | I want to suggest and advertize/post related events to AGRODEP calendar | events | low |  | x | x | x | x | x | x | 45 | 5 | 100% | feature currently limited to staff members but can easily be opened to all members.
R11 | I want to consult and download AGRODEP key output (publications, reports, public datasets, public models, graphs and maps) | output | high | x | x | x | x | x | x | x | 1 | 2 | 100% | data entry forms are functional - front-end needs design improvements
R12 | I want a searchable, categorized inventory of all AGRODEP models (both public and private) and of relevant models available on external websites | model repository | high | x | x | x | x | x | x | x | 2 | 2 | 100% | feature is built. A majority of models are currently missing.
R13 | I want to know the development status of AGRODEP models (version number, version history, roadmap, associated documentation and discussion threads) | model repository | high | x | x | x | x | x | x | x | 35 | TBD | 100% | Dataverse option was dropped - versioning and documentation in Drupal - model packages are not ready yet - Wiki feature is working.
R14 | I want to download the latest version or earlier snapshots of AGRODEP models | model repository | high |  | x | x | x | x | x | x | x | 2 | 100% | through Drupal instead of Dataverse
R15 | I want to comment on model development, submit issues or change/improvement requests | model repository | medium |  | x | x | x | x | x | x | 29 | 1 | 100% | achieved through Wiki feature
R16 | I want to upload new model packages (new models, or new versions of existing models, or branched models) | model repository | high |  |  |  |  | x | x |  | 3 | TBD | 100% | limited to Research Team initially but expanded to all members in later phase
R16.1 | I want to categorize and tag uploaded models (according to AGRODEP taxonomy) | model repository | high |  |  |  |  | x | x |  | 4 | 2 | 100% | initial taxonomy to be discussed
R17 | I want to contribute to model documentation through a collaborative wiki | model repository | high |  | x | x | x | x | x | x | 19 | 5 | 100% | wiki-like functionality needed to support collaborative editing
R18 | I want to suggest new models for inclusion on AGRODEP website | model repository | low |  | x | x | x | x | x |  | 30 | TBD | 100% | through AGRODEP Blog (no special feature)
R19 | I want a searchable, categorized a list of model applications (abstract, associated paper(s), results sets and graphs/maps) | application repository | high | x | x | x | x | x | x | x | 8 | 2 | 100% | through Documents section - need design improvements
R20 | I want to suggest new model applications for inclusion on AGRODEP website | application repository | low |  | x | x | x | x | x | x | 32 | 3 | 100% | through AGRODEP Blog (no special feature)
R21 | I want to upload new model applications (file package, paper, documentation, datasets, graphs and maps) | application repository | high |  |  |  |  | x | x |  | 9 | 2 | 100% | limited to Research Team initially but expanded to all members in later phase
R21.1 | I want to categorize and tag uploaded applications (according to AGRODEP taxonomy) | application repository | high |  |  |  |  | x | x |  | 10 | 2 | 100%
R22 | I want to comment on individual model applications and read other's comments | application repository | medium |  | x | x | x | x | x | x | 31 | 1 | 100% | through AGRODEP Blog
R23 | I want a searchable, categorized inventory of AGRODEP dataset packages and of relevant datasets available on external websites. | data repository | high | x | x | x | x | x | x | x | 5 | TBD | 100% | feature is built to Drupal. Content loading is on-going.
R24 | I want to know the development status of AGRODEP datasets (version number, version history, roadmap, associated documentation and discussion threads) | data repository | high | x | x | x | x | x | x | x | 36 | TBD | 100% | Wiki
R25 | I want to download the latest version or earlier snapshots of AGRODEP datasets | data repository | high |  | x | x | x | x | x | x | x | TBD | 100%
R26 | I want to comment on dataset development, submit issues or change/improvement requests | data repository | medium |  | x | x | x | x | x | x | 34 | 1 | 100% | thrugh AGRODEP Wiki or Blog.
R27 | I want to upload new datasets (new or new version of existing sets) | data repository | high |  |  |  |  | x | x |  | 6 | 2 | 100% | limited to Research Team initially but expanded to all members in later phase
R27.1 | I want to categorize and tag uploaded datasets (according to AGRODEP's taxonomy) | data repository | high |  |  |  |  | x | x |  | 7 | 1 | 100%
R28 | I want to contribute to dataset documentation through a collaborative wiki | data repository | high |  | x | x | x | x | x | x | 33 | 5 | 100% | wiki-like functionality needed to support collaborative editing
R29 | I want to consult a list of applications using a particular dataset (abstract, associated paper(s), results sets and graphs/maps) | data repository | medium |  | x | x | x | x | x | x | 38 | 2 | 100% | Linkages between applications and datasets are built-in but need to be entered manually.
R30 | I want to consult a list of models having a particular dataset as input | data repository | medium |  | x | x | x | x | x | x | 39 | 2 | 100% | Linkages between models and datasets are built-in but need to be entered manually.
R31 | I want a link to the model (if any) that generated a particular dataset | data repository | medium |  | x | x | x | x | x | x | 40 | 1 | 100% | Linkages between models and datasets are built-in but need to be entered manually.
R32 | I want to suggest new datasets for inclusion on AGRODEP website | data repository | low |  | x | x | x | x | x |  | 41 | 3 | 100% | through AGRODEP Blog
R33 | I want a private area to discuss and report on governance activities and share files with members of the Advisory Board and Steering Committee | governance | high |  |  | x | x | x | x |  | 42 | 8 | 100% | through Governance Blog and Wiki
R34 | I want to feature specific model(s), model application(s) and/or datasets, event(s) and/or member(s) on AGRODEP website | content management | high | [5 empty] | x |  | 28 | 2 | 100%
R35 | I want to create, update user profiles and invite new members to join in | administration | high | [5 empty] | x |  | 26 | 1 | 100% | users can edit their own profile, AGRODEP staff can edit all profiles.
R36 | I want to control group memberships and group permissions | administration | high | [5 empty] | x |  | 27 | 1 | 100%
R37 | I want to assign and modify tags to website pages and attachments, models, datasets, and model applications | content management | medium |  | x | x | x | x | x |  | 22 | 3 | 80% | no user-defined "tags" or keyowrds built in yet. May be added easily.
R38 | I want to control membership to AGRODEP mailing lists | administration | high | [5 empty] | x |  | 44 | 1 | -- | continue using MailChimp to maintain all mailing lists (could use a CGIAR distribution list instead if that's easier to maintain).
R39 | I want to add new and modify existing pages on AGRODEP website | content management | high | [5 empty] | x |  | 23 | 1 | 100%
R39.1 | I want to modify AGRODEP taxonomies (add/remove/reorder terms) | content management | high | [5 empty] | x |  | 24 | 1 | 100%
R40 | I want options to backup and restore snapshots of AGRODEP website | administration | medium | [5 empty] | x |  | 45 | 1 | 100% | server backups (with code base) more reliable than Drupal database snapshots.
R41 | I want to mark members who are registered to specific events and members who attended specific events | administration | medium |  |  |  |  | x | x |  | 25 | TBD | 50% | status currently does not show "applied" or "registered", only "attended".
R42 | I want to select one or more country(ies) on a map and view AGRODEP collections for that country(ies) in a categorized list (models, datasets, applications/publications) showing item count and list of top/recent items (with links to see more details) | visualization | high | x | x | x | x | x | x | x | 21 | 5 | 100%
R43 | I want to select one or more categories of items in AGRODEP collections (families of model, categories of datasets, applications and application's main topics) and see the corresponding geographic coverage for that category(ies) on a map | visualization | high | x | x | x | x | x | x | x | 20 | TBD | 50% | in process
R44 | I want to load a series of model simulation results in MSExcel (or CSV) format and select which variables/scenarios to chart and compare | visualization | high |  | x | x | x | x | x |  |  | MappingWorlds | ? | needs testing
R45 | I want to save and describe (title, metadata) the uploaded dataset for later re-use | visualization | high |  | x | x | x | x | x |  |  | MappingWorlds | ? | needs testing
R46 | I want to draw up to 2 static variables across 2 scenarios on either a bar or area (more…) chart | visualization | high |  | x | x | x | x | x |  |  | MappingWorlds | ? | needs testing
R47 | I want to draw up to 2 time-series variables across 2 scenarios on either a bar or area (more…) chart with a dynamic time slider | visualization | medium |  | x | x | x | x | x |  |  | MappingWorlds | ? | needs testing
R48 | I want to draw up to 2 time-series variables across 2 scenarios on a line chart | visualization | medium |  | x | x | x | x | x |  |  | MappingWorlds | ? | needs testing
R49 | I want to select and map 1 variable and 1 scenario and compare results across countries or regions on a map | visualization | medium |  | x | x | x | x | x |  |  | MappingWorlds | ? | needs testing
R50 | I want to select 1 variable from 1 scenario, pick a country on a map and display the flow arrows from/to that country (with arrow width proportional to value) | visualization | medium |  | x | x | x | x | x |  |  | MappingWorlds | ? | needs testing
R51 | I want to embed my custom chart into AGRODEP's website | visualization | high |  | x | x | x | x | x |  |  | MappingWorlds | ? | needs testing
R52 | I want to export my custom chart as PNG | visualization | high |  | x | x | x | x | x |  |  | MappingWorlds | ? | needs testing
R53 | I want to export the chart data in a tabular format (XLS or CSV) | visualization | medium |  | x | x | x | x | x |  |  | MappingWorlds | ? | needs testing
R54 | I want to be able to re-use data previously loaded and saved in the charting interface | visualization | medium |  | x | x | x | x | x |  |  | MappingWorlds | ? | needs testing